## Assignment Template
| Duration | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20
Task | (In Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
Phase 1: Use the training data to develop an algorithm for determining if a water pump is functional, non functional, or needs repair | 10 | bar: Week 1 1 to Week 2 10
Data Understanding
Create visual defining each variable and applicable terminology. | 1 | bar: Week 1 1
Start cleaning data by removing variables that are redundant and then review the remaining variables for outliers or inaccurate data. | 3 | bar: Week 1 2 to Week 1 4
Investigate the correlation between the variables in the training set data to the training labels data to determine which variables are most highly correlated with 'functional', 'non functional', and 'functional needs repair'. | 2 | bar: Week 1 5 to Week 2 6
Investigate the correlation between the other variables and the variables most highly correlated with 'functional', 'non functional', and 'functional needs repair' to figure out which variables should be included in an algorithm | 2 | bar: Week 2 7 to Week 2 8
Create potential algorithm to determine if a water pump is 'functional', 'non-functional', and 'functional needs repair' | 2 | bar: Week 2 9 to Week 2 10
Phase 2: Use algorithm on test data to determine which level each water pump is at and use data to investigate non functional and then functional needs repair water pumps | 32 | bar: Week 3 11 to Week 9 42
Business Understanding
Create a visual of what constitutes 'functional', 'non-functional', and 'functional needs repair' categories based on examples (water quality and water quantity examples) | 2 | bar: Week 3 11 to Week 3 12
Create visual of current water pump state, showing how many water pumps are non functional or functional but needing repairs based on the training set data to provide a baseline average | 2 | bar: Week 3 13 to Week 3 14
Research how long it typically takes for water pumps to be repaired as well as the impact on communities while they are waiting for the repairs | 4 | bar: Week 3 15 to Week 4 18
Create and present the visual of water pump categories, training set averages, and the research about the community impact and time it takes to delegate water pump repairs currently to Taarifa | 5 | bar: Week 4 19 to Week 5 23
Data Understanding
Test algorithm on three sets of 1000 randomly selected data points from the training data and evaluate accuracy by comparing algorithm result to training labels. | 3 | bar: Week 5 24 to Week 6 26
Refine algorithm to figure out which variables contribute most to the accuracy of the model and retest until each test has 80% or above accuracy | 5 | bar: Week 6 27 to Week 7 31
Data Preparation
Use the algorithm to sort the test data into categories | 1 | bar: Week 7 32
Modeling
Create model showing the accuracy of the algorithm on the training data by each category | 2 | bar: Week 7 33 to Week 7 34
Create model of the test data categories (excel sheet with water point ID and label as a deliverable) | 1 | bar: Week 7 35
Evaluation
Create presentation and present the results showing the accuracy of the model including examples of where the model was accurate and where weaknesses lie and can be improved | 5 | bar: Week 8 36 to Week 8 40
Create visual comparing test data categories compared to the training set data categories | 2 | bar: Week 9 41 to Week 9 42
Continue improving algorithm as new data is gathered and meet when new versions are used and explain reasons why it is an improvement | Ongoing